## Project Timeline
Project Timeline & Milestone Tracker
Task | Phase | Owner | Start Date | End Date | Duration (days) | % Complete | Status | Dependencies
Project Kickoff | Planning | Alice | 2025-01-06 | 2025-01-07 |  | 0% | Discovery
Requirements Gathering | Planning | Bob | 2025-01-08 | 2025-01-17 |  | 85% | Complete | Task 1
UI/UX Design | Design | Carol | 2025-01-20 | 2025-02-07 |  | 70% | In Progress | Task 2
Database Architecture | Development | Dave | 2025-01-20 | 2025-01-31 |  | 100% | Complete | Task 2
Backend API Development | Development | Dave | 2025-02-03 | 2025-02-28 |  | 60% | In Progress | Task 4
Frontend Development | Development | Carol | 2025-02-10 | 2025-03-14 |  | 40% | In Progress | Task 3
Integration & Testing | Testing | Alice | 2025-03-17 | 2025-03-28 |  | 0% | Not Started | Task 5,6
UAT (User Acceptance) | Testing | Bob | 2025-03-31 | 2025-04-11 |  | 0% | Not Started | Task 7
Deployment & Launch | Launch | Alice | 2025-04-14 | 2025-04-18 |  | 0% | Not Started | Task 8
Post-Launch Review | Launch | Team | 2025-04-21 | 2025-04-25 |  | 0% | Not Started | Task 9
OVERALL PROGRESS